## Sheet1
| October | [11 empty] | November | [29 empty] | December | [7 empty] | Legend:
| Week 1 |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 |  |  |  |  | Color | Group Responsible
| F | S | Su | M | Tu | W | Th | F | S | Su | M | Tu | W | Th | F | S | Su | M | Tu | W | Th | F | S | Su | M | Tu | W | Th | F | S | Su | M | Tu | W | Th | F | S | Su | M | Tu | W | Th | F | S | Su | M | Tu | W | Th | F |  | Entire Team
General | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | Giovanni Artavia & Brandon Lammey
Choose Project | [51 empty] | Dylan Herrig & James Glass | bar: Week 1 F to Week 1 S
Understand basic Swift | bar: Week 1 Su
Design Project | bar: Week 1 Su to Week 2 M
Divvy Up Tasks | bar: Week 2 M
Group Program Meets | bar: Week 2 Su; Week 3 Su; Week 4 Su; Week 5 Su; Week 6 Su; Week 7 Su
Status Meets | bar: Week 2 W; Week 2 F; Week 3 M; Week 3 W; Week 3 F; Week 4 M; Week 4 W; Week 4 F; Week 5 M; Week 5 W; Week 5 F; Week 6 M; Week 6 W; Week 6 F; Week 7 M; Week 7 W; Week 7 F; Week 8 M; Week 8 W; Week 8 F
Screens
Welcome Screen
Start Game button | bar: Week 2 M
Tutorial Button | bar: Week 3 W
Tutorial Screen
Tutorial Information | bar: Week 3 Tu to Week 3 W
Forward and Back buttons | bar: Week 3 W
Coin Flip Screen
Coin Flip Function | bar: Week 3 W
Player Class Screen
Select class options | bar: Week 3 M
Game Playing screen
Shuffle cards | bar: Week 2 W
Player Mode | bar: Week 2 M
Player class | bar: Week 2 M
Card effects | bar: Week 2 M to Week 2 Th
View Controllers in Game Playing Screen | bar: Week 2 W to Week 2 F; Week 3 Tu to Week 3 W
Game Over Screen
Restart | bar: Week 2 F
Assets
Button Assets | bar: Week 1 F; Week 2 M to Week 2 Tu; Week 2 S to Week 2 Su
Logo Asset | bar: Week 2 S to Week 2 Su
App Icon Asset | bar: Week 2 M to Week 2 Tu
Card art Assets | bar: Week 2 M to Week 2 Tu; Week 2 S to Week 2 Su
Health Bar Asset | bar: Week 2 W; Week 2 F
Stamina Bar Asset | bar: Week 2 W; Week 2 F
Attack Bar Asset | bar: Week 2 W; Week 2 F
Coin Asset | bar: Week 2 Su
Player Class Picture Assets | bar: Week 2 Su
Animations
Deck/Class Idle Animations | bar: Week 4 M to Week 4 Tu
Shuffle Animation | bar: Week 3 Th
Attack Animations | bar: Week 6 S to Week 6 Su; Week 7 S to Week 7 Su
Zoom animation | bar: Week 3 Th; Week 5 F to Week 5 S
Project 4 Plans
Test Functions | bar: Week 3 Tu to Week 3 W; Week 4 M to Week 4 W; Week 5 M to Week 5 W; Week 6 M to Week 6 W; Week 7 M to Week 7 W; Week 8 M to Week 8 W
Surrender Screen( from menu button) | bar: Week 4 M to Week 4 Tu
Add new decks | bar: Week 4 F to Week 4 S; Week 5 S to Week 5 Su; Week 6 S to Week 6 Su; Week 7 S to Week 7 Su
Online capability | bar: Week 3 S to Week 4 W
Timer for online | bar: Week 4 Tu to Week 4 Th
Tutorial (Possible in-game tutorial) | bar: Week 6 M to Week 6 W
Orientation Options | bar: Week 6 S to Week 6 Su
Sounds Assets | bar: Week 7 Su to Week 8 Tu
Multiple Devices Support | bar: Week 6 S to Week 6 Su
Pausing Functionality | bar: Week 6 M to Week 6 W; Week 7 M to Week 7 W
Deck Building | bar: Week 5 M to Week 5 W; Week 6 M to Week 6 W; Week 7 M to Week 7 W; Week 7 Su to Week 8 Tu

## Form Responses 1
Timestamp | Untitled Question